## Test report
Test report
Project Name | Calculation software
Stage | Sprint 1
Project Code
Test Environment Setup Description | Winform
Tester | Trần Mai Huy Hoàng
Test Result | PASS
FAIL
SKIPPED
NOT IMPLEMENTED
No | Testcase ID | Function Name | Sheet Name | Create Date
1 | A - X | Addition | Addition Function | 2024-02-16
2 | S - X | Subtraction | Subtraction Function | 2024-02-16
3 | M - X | Multiplication | Multiplication Function | 2024-02-16
4 | D - X | Division | Division Function | 2024-02-16
5 | M - X | Modulus | Modulus Function | 2024-02-16
6 | C - X | Clear | Clear Function | 2024-02-16
Note: X is Number

## Addition Function
Module |  | Addition
Code |  | AC
Check requirement
Tester |  | Trần Mai Huy Hoàng
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 16 | 14 | 2 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 16 | 14 | 2 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | AC - 1 | Addition | Check Radio button |  | 1. Click on rdAdd(radio button) 2. Choose "Addition" in Radio Button. |  | Enter correct values A,B | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
2 | AC - 2 | Addition | Enter value |  | 1. Click on text file of number A and number B . 2. Enter the value. | Number A ="13" Number B = "A" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
3 | AC - 3 | Addition | Enter check number |  | 1. Click on text file of number A and number B . 2. Enter the value. 3. Click on Calculate(CAL). | Number A ="13" Number B = "A" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
4 | AC - 4 | Addition | Calculate |  | 1. Click on Calculate(CAL). | Number A ="13" Number B = "A" result = One of the two is not the same | The result is incorrect | 2024-02-10 | FAIL |  | FAIL | Trần Mai Huy Hoàng
5 | AC - 5 | Addition | Enter value |  | 1. Click on text file of number A and number B . 2. Enter the value. | Number A ="67" Number B = "13" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
6 | AC - 6 | Addition | Enter check number |  | 1. Click on text file of number A and number B . 2. Enter the value. 3. Click on Calculate(CAL). | Number A ="67" Number B = "13" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
7 | AC - 7 | Addition | Calculate |  | 1. Click on Calculate(CAL). | Number A ="67" Number B = "13" result = 80 | The result is correct | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
8 | AC - 8 | Addition | Enter value |  | 1. Click on text file of number A and number B . 2. Enter the value. | Number A ="15" Number B = "2" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
9 | AC - 9 | Addition | Enter check number |  | 1. Click on text file of number A and number B . 2. Enter the value. 3. Click on Calculate(CAL). | Number A ="15" Number B = "2" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
10 | AC - 10 | Addition | Calculate |  | 1. Click on Calculate(CAL). | Number A ="15" Number B = "2" result = 17 | The result is correct | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
11 | AC - 11 | Addition | Enter value |  | 1. Click on text file of number A and number B . 2. Enter the value. | Number A ="38" Number B = "42" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
12 | AC - 12 | Addition | Enter check number |  | 1. Click on text file of number A and number B . 2. Enter the value. 3. Click on Calculate(CAL). | Number A ="38" Number B = "42" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
13 | AC - 13 | Addition | Calculate |  | 1. Click on Calculate(CAL). | Number A ="38" Number B = "42" result = 80 | The result is correct | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
14 | AC - 14 | Addition | Enter value |  | 1. Click on text file of number A and number B . 2. Enter the value. | Number A ="a" Number B = "b" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
15 | AC - 15 | Addition | Enter check number |  | 1. Click on text file of number A and number B . 2. Enter the value. 3. Click on Calculate(CAL). | Number A ="a" Number B = "b" |  | 2024-02-10 | PASS |  | PASS | Trần Mai Huy Hoàng
16 | AC - 16 | Addition | Calculate |  | 1. Click on Calculate(CAL). | Number A ="a" Number B = "b" result = One of the two is not the same | The result is incorrect | 2024-02-10 | FAIL |  | FAIL | Trần Mai Huy Hoàng

## Subtraction Function
Module |  | Subtraction
Code |  | SC
Check requirement
Tester |  | Tran Mai Huy Hoang
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 12 | 11 | 1 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 12 | 11 | 1 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | SC - 1 | Subtraction | Check Radio button |  | 1. Click on rdSub(radio button) 2. Choose "Subtraction" in Radio Button. |  | Enter correct values A,B | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
2 | SC - 2 | Subtraction | Enter value |  | 1. Click on text file of number A and number B. 2. Enter the value. | Number A ="35" Number B = "15" | Input number on text file | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
3 | SC - 3 | Subtraction | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="35" Number B = "15" | Input in text field must a number . | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
4 | SC - 4 | Subtraction | Calculate |  | 1. Click on Calculate. | Number A ="35" Number B = "15" result = 20 | The result is correct | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
5 | SC - 5 | Subtraction | Check Radio button |  | 1. Click on rdSub(radio button) 2. Choose "Subtraction" in Radio Button. |  | Enter correct values A,B | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
6 | SC - 6 | Subtraction | Enter value |  | 1. Click on text file of number A and number B. 2. Enter the value. | Number A ="78" Number B = "A" | Input number on text file | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
7 | SC - 7 | Subtraction | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="78" Number B = "A" | Input in text field must a number . | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
8 | SC - 8 | Subtraction | Calculate |  | 1. Click on Calculate. | Number A ="78" Number B = "A" result = One of the two is not the same | The result is correct | 2024-02-11 | FAIL |  | FAIL | Tran Mai Huy Hoang
9 | SC - 9 | Subtraction | Check Radio button |  | 1. Click on rdSub(radio button) 2. Choose "Subtraction" in Radio Button. |  | Enter correct values A,B | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
10 | SC - 10 | Subtraction | Enter value |  | 1. Click on text file of number A and number B. 2. Enter the value. | Number A ="58" Number B = "16" | Input number on text file | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
11 | SC - 11 | Subtraction | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="58" Number B = "16" | Input in text field must a number . | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang
12 | SC - 12 | Subtraction | Calculate |  | 1. Click on Calculate. | Number A ="58" Number B = "16" result = 42 | The result is correct | 2024-02-11 | PASS |  | PASS | Tran Mai Huy Hoang

## Multiplication Function
Module |  | Multiplication
Code |  | MC
Check requirement
Tester |  | Trần Mai Huy Hoàng
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 12 | 12 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 12 | 12 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | MC - 1 | Multiplication | Check Radio button |  | 1. Click on rdMul(radio button) 2. Choose "Multiplication" in Radio Button. |  | Enter correct values A,B | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
2 | MC - 2 | Multiplication | Enter value |  | 1. Click on text file of number A and number B. 2. Enter the value. | Number A ="45" Number B = "1" | Input number on text box | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
3 | MC - 3 | Multiplication | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="45" Number B = "1" | Input in text field must a number . | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
4 | MC - 4 | Multiplication | Calculate |  | 1. Click on Calculate. | Number A ="45" Number B = "1" Result = 45 | The result is correct | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
5 | MC - 5 | Multiplication | Check Radio button |  | 1. Click on rdMul(radio button) 2. Choose "Multiplication" in Radio Button. |  | Enter correct values A,B | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
6 | MC - 6 | Multiplication | Enter value |  | 1. Click on text file of number A and number B. 2. Enter the value. | Number A ="59" Number B = "57" | Input number on text box | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
7 | MC - 7 | Multiplication | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="59" Number B = "57" | Input in text field must a number . | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
8 | MC - 8 | Multiplication | Calculate |  | 1. Click on Calculate. | Number A ="59" Number B = "57" Result = 3363 | The result is correct | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
9 | MC - 9 | Multiplication | Check Radio button |  | 1. Click on rdMul(radio button) 2. Choose "Multiplication" in Radio Button. |  | Enter correct values A,B | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
10 | MC - 10 | Multiplication | Enter value |  | 1. Click on text file of number A and number B. 2. Enter the value. | Number A ="26" Number B = "2" | Input number on text box | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
11 | MC - 11 | Multiplication | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="26" Number B = "2" | Input in text field must a number . | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang
12 | MC - 12 | Multiplication | Calculate |  | 1. Click on Calculate. | Number A ="26" Number B = "2" Result = 52 | The result is correct | 2024-02-12 | PASS |  | PASS | Tran Mai Huy Hoang

## Division Function
Module |  | Division
Code |  | CD
Check requirement
Tester |  | Trần Mai Huy Hoàng
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 17 | 17 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 17 | 17 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | CD - 1 | Division | Check Radio button |  | 1. Click on rdDivl(radio button) 2. Choose "Divison" in Radio Button. |  | Enter correct values A,B | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
2 | CD - 2 | Division | Enter value |  | 1. Click on text file of Number A and Number B. 2. Enter the value. | Number A ="19" Number B = "11" | Input number on text box | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
3 | CD - 3 | Division | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="40" Number B = "5" | Input in text field must a number ". | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
4 | CD - 4 | Division | Calculate |  | 1. Click on text file of number A and number B. 2. Enter the value. 3. Click on Calculate. | Number A ="40" Number B = "0" | Cannot be divided by 0 | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
5 | CD - 5 | Division | Calculate |  | 1. Click on Calculate. | Number A ="40" Number B = "5" Result =8 | The result is correct | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
2 | CD - 2 | Division | Enter value |  | 1. Click on text file of Number A and Number B. 2. Enter the value. | Number A ="19" Number B = "11" | Input number on text box | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
3 | CD - 3 | Division | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="40" Number B = "5" | Input in text field must a number ". | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
4 | CD - 4 | Division | Calculate |  | 1. Click on text file of number A and number B. 2. Enter the value. 3. Click on Calculate. | Number A ="40" Number B = "0" | Cannot be divided by 0 | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
5 | CD - 5 | Division | Calculate |  | 1. Click on Calculate. | Number A ="40" Number B = "5" Result =8 | The result is correct | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
2 | CD - 2 | Division | Enter value |  | 1. Click on text file of Number A and Number B. 2. Enter the value. | Number A ="19" Number B = "11" | Input number on text box | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
3 | CD - 3 | Division | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="40" Number B = "5" | Input in text field must a number ". | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
4 | CD - 4 | Division | Calculate |  | 1. Click on text file of number A and number B. 2. Enter the value. 3. Click on Calculate. | Number A ="40" Number B = "0" | Cannot be divided by 0 | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
5 | CD - 5 | Division | Calculate |  | 1. Click on Calculate. | Number A ="40" Number B = "5" Result =8 | The result is correct | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
2 | CD - 2 | Division | Enter value |  | 1. Click on text file of Number A and Number B. 2. Enter the value. | Number A ="19" Number B = "11" | Input number on text box | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
3 | CD - 3 | Division | Enter check number |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="40" Number B = "5" | Input in text field must a number ". | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
4 | CD - 4 | Division | Calculate |  | 1. Click on text file of number A and number B. 2. Enter the value. 3. Click on Calculate. | Number A ="40" Number B = "0" | Cannot be divided by 0 | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng
5 | CD - 5 | Division | Calculate |  | 1. Click on Calculate. | Number A ="40" Number B = "5" Result =8 | The result is correct | 2024-02-13 | PASS |  | PASS | Trần Mai Huy Hoàng

## Modulus Function
Module |  | Modulus
Code |  | MC
Check requirement
Tester |  | Dabg Quoc Dinh
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 5 | 5 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | MC - 1 | Modulus | Check Radio button |  | 1. Click on rdMod(radio button) 2. Choose "Divison" in Radio Button. |  | Enter correct values A,B | 2024-02-14 | PASS |  | PASS | Trần Mai Huy Hoàng
2 | MC - 2 | Modulus | Enter value |  | 1. Click on text file of Number A and Number B. 2. Enter the value. | Number A ="16" Number B = "3" | Input number on text box | 2024-02-14 | PASS |  | PASS | Trần Mai Huy Hoàng
3 | MC - 3 | Modulus | Enter check number |  | 1. Click on text file of number A and number B. 2. Enter the value. 3. Click on Calculate. | Number A ="16" Number B = "3" | Input in text field must a number ". | 2024-02-14 | PASS |  | PASS | Trần Mai Huy Hoàng
4 | MC - 4 | Modulus | Calculate |  | 1. Click on text file of Number A and Number B. 2. Enter the value. 3. Click on Calculate. | Number A ="16" Number B = "0" | Cannot be modulus by 0 | 2024-02-14 | PASS |  | PASS | Trần Mai Huy Hoàng
5 | MC - 5 | Modulus | Calculate |  | 1. Click on Calculate. | Number A ="16" Number B = "3" result = 1 | The result is correct | 2024-02-14 | PASS |  | PASS | Trần Mai Huy Hoàng

## Clear Function
Module |  | Reset
Code |  | R
Check requirement
Tester |  | Trần Mai Huy Hoàng
Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 1 | 1 | 0 | 0 | 0
Re-test Status |  | TOTAL | PASS | FAIL | Not Implemented | SKIPPED
|  | 1 | 1 | 0 | 0 | 0
STT | Test case ID | Requirements ID | Test case decription | Pre - Condition | Step | Data | Excepted Result | Test Date | Actual Result | Re-test Date | Re-test Result | Assign to
1 | R - 1 | Reset | Reset the value |  | 1. Click on "Reset" button. |  | The value not reset | 2024-02-17 | PASS |  | PASS | Trần Mai Huy Hoàng