## Participants
Inspection Roles
No | Group Member | Roles | Comment
1 | Nguyen Bui Ngoc Hoa | Moderator
2 | Tran Mai Huy Hoang | Inspector
3 | Thai Duy Vu | Inspector
4 | Vo Phi Hung | Inspector
5 | Kim Ngoc Viet Toan | Inspector
6 | Pham Minh Trang | Inspector

## Schedules
Inspection Schedule
No | Task | Task owner | Start time | End time | Comment
1 | Review PROJETC PLAN DOCUMENT | Nguyen Bui Ngoc Hoa | 23/02/2024 | 24/02/2024
2 | Review SOFTWARE REQUIREMENT SPECIFICATION DOCUMENT | Tran Mai Huy Hoang, Kim Ngoc Viet Toan | 24/02/2024 | 25/02/2024
3 | Review DEFINDED PROCESS DOCUMENT | Vo Phi Hung | 25/02/2024 | 26/02/2024
4 | Review CODE | Nguyen Bui Ngoc Hoa, Thai Duy Vu | 26/02/2024 | 27/02/2024
5 | Review TEST CASE | Nguyen Bui Ngoc Hoa | 27/02/2024 | 28/02/2024
6 | Review USER INTERFACE DESIGN DOCUMENT | Pham Minh Trang | 28/02/2024 | 29/02/2024

## Materials
Inspection Material
No | Tool/Material | Quantity | Comment
1 | Apache NetBeans | 6
2 | Word | 6
3 | Excel | 2
4 | Laptop | 6